## Timeline
Board - RAD Project (by days)
|  |  | May-2020 | May-2020 | May-2020 | May-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jun-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020 | Jul-2020
| Start | End | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
groups - Sprint One |  |  | 28: groups - Sprint One
Allocating roles and tasks | 28-May-2020 | 28-May-2020 | 28: Allocating roles and tasks (28-May-20 - 28-May-20)
Decide the version of User Interface | 28-May-2020 | 28-May-2020 | 28: Decide the version of User Interface (28-May-20 - 28-May-20)
Create Project Management Plan | 28-May-2020 | 31-May-2020 | 28: Create Project Management Plan (28-May-20 - 31-May-20); 29: Create Project Management Plan (28-May-20 - 31-May-20); 30: Create Project Management Plan (28-May-20 - 31-May-20); 31: Create Project Management Plan (28-May-20 - 31-May-20)
Create GitHub Team | 28-May-2020 | 31-May-2020 | 28: Create GitHub Team (28-May-20 - 31-May-20); 29: Create GitHub Team (28-May-20 - 31-May-20); 30: Create GitHub Team (28-May-20 - 31-May-20); 31: Create GitHub Team (28-May-20 - 31-May-20)
Snapshot of Source Control | 28-May-2020 | 02-Jun-2020 | 28: Snapshot of Source Control (28-May-20 - 02-Jun-20); 29: Snapshot of Source Control (28-May-20 - 02-Jun-20); 30: Snapshot of Source Control (28-May-20 - 02-Jun-20); 31: Snapshot of Source Control (28-May-20 - 02-Jun-20); 1: Snapshot of Source Control (28-May-20 - 02-Jun-20); 2: Snapshot of Source Control (28-May-20 - 02-Jun-20)
Create Testing Plan | 28-May-2020 | 02-Jun-2020 | 28: Create Testing Plan (28-May-20 - 02-Jun-20); 29: Create Testing Plan (28-May-20 - 02-Jun-20); 30: Create Testing Plan (28-May-20 - 02-Jun-20); 31: Create Testing Plan (28-May-20 - 02-Jun-20); 1: Create Testing Plan (28-May-20 - 02-Jun-20); 2: Create Testing Plan (28-May-20 - 02-Jun-20)
Compose Analysis Report | 28-May-2020 | 02-Jun-2020 | 28: Compose Analysis Report (28-May-20 - 02-Jun-20); 29: Compose Analysis Report (28-May-20 - 02-Jun-20); 30: Compose Analysis Report (28-May-20 - 02-Jun-20); 31: Compose Analysis Report (28-May-20 - 02-Jun-20); 1: Compose Analysis Report (28-May-20 - 02-Jun-20); 2: Compose Analysis Report (28-May-20 - 02-Jun-20)
Multi-Platform Report | 28-May-2020 | 02-Jun-2020 | 28: Multi-Platform Report (28-May-20 - 02-Jun-20); 29: Multi-Platform Report (28-May-20 - 02-Jun-20); 30: Multi-Platform Report (28-May-20 - 02-Jun-20); 31: Multi-Platform Report (28-May-20 - 02-Jun-20); 1: Multi-Platform Report (28-May-20 - 02-Jun-20); 2: Multi-Platform Report (28-May-20 - 02-Jun-20)
Review all tasks | 02-Jun-2020 | 02-Jun-2020 | 2: Review all tasks (02-Jun-20 - 02-Jun-20)
Presentation | 04-Jun-2020 | 04-Jun-2020 | 4: Presentation (04-Jun-20 - 04-Jun-20)
Mario
Chen
John
All